## ProjectSchedule
SWYL - Support Who You Love
| Logan Nguyen | Project Start: | 2022-08-22
|  | Today: | 2022-10-14
|  | Display Week: | 1 |  |  | 2022-08-22 | [6 empty] | 2022-08-29 | [6 empty] | 2022-09-05 | [6 empty] | 2022-09-12 | [6 empty] | 2022-09-19 | [6 empty] | 2022-09-26 | [6 empty] | 2022-10-03 | [6 empty] | 2022-10-10 | [6 empty] | 2022-10-17 | [6 empty] | 2022-10-24 | [6 empty] | 2022-10-31 | [6 empty] | 2022-11-07 | [6 empty] | 2022-11-14 | [6 empty] | 2022-11-21 | [6 empty] | 2022-11-28
 | time axis 2022-08-22 to 2022-12-04
| TASK | PROGRESS | START | END | DAYS | time axis 2022-08-22 to 2022-12-04
Phase 1: Project Scoping
| Project Start | 100% | 2022-08-26 | 2022-09-15 | bar: 2022-08-22 to 2022-09-15
| Vision Statement | 100% | 2022-08-26 | 2022-09-11 | 17 | bar: 2022-08-22 to 2022-09-15
| Draft Personas | 100% | 2022-08-29 | 2022-09-12 | bar: 2022-08-22 to 2022-09-15
| Draft Users stories | 100% | 2022-08-29 | 2022-09-12 | bar: 2022-08-22 to 2022-09-15
| Project Scope and Project Pitch | 100% | 2022-08-29 | 2022-09-11 | 14 | bar: 2022-08-22 to 2022-09-15
| Project Tech Choices draft v1.0 | 100% | 2022-09-11 | 2022-09-15 | 5 | bar: 2022-08-22 to 2022-09-15
| Draft SRS Docs v1.0 | 100% | 2022-09-18 | 2022-09-25 | bar: 2022-08-22 to 2022-09-25
| SRS - Product_Overview | 100% | 2022-09-18 | 2022-09-19 | bar: 2022-08-22 to 2022-09-25
| SRS - Functional_Interfaces | 100% | 2022-09-19 | 2022-09-20 | bar: 2022-08-22 to 2022-09-25
| SRS - Function_requirements | 100% | 2022-09-20 | 2022-09-22 | bar: 2022-08-22 to 2022-09-25
| SRS - Analysis_models (AM) | 100% | 2022-09-22 | 2022-09-25 | bar: 2022-08-22 to 2022-09-25
| AM - Use _case_diagrams | 100% | 2022-09-22 | 2022-09-23 | bar: 2022-08-22 to 2022-09-25
| AM - Activity_diagrams | 100% | 2022-09-23 | 2022-09-24 | bar: 2022-08-22 to 2022-09-25
| AM - System_Architechtures | 100% | 2022-09-24 | 2022-09-25 | bar: 2022-08-22 to 2022-09-25
| Draft SRS Docs v2.0 | 100% | 2022-09-26 | 2022-09-28 | bar: 2022-08-22 to 2022-09-28
| SRS_v2.0 - Revise User Stories + Features | 100% | 2022-09-26 | 2022-09-27 | bar: 2022-08-22 to 2022-09-28
| SRS_v2.0 - Revise Analysis models diagrams | 100% | 2022-09-27 | 2022-09-28 | bar: 2022-08-22 to 2022-09-28
Draft SRS Docs v2.0 | Draft SRS Docs v3.0 | 100% | 2022-10-03 | 2022-10-03 | bar: 2022-08-22 to 2022-10-03
SRS.v2.0 - Revise User Stories + Features | SRS_v3.0 - Revise User Stories + Features | 100% | 2022-10-03 | 2022-10-03 | bar: 2022-08-22 to 2022-10-03
SRS.v2.0 - Revise Analysis models diagrams | SRS_v3.0 - Revise Analysis models diagrams | 100% | 2022-10-03 | 2022-10-03 | bar: 2022-08-22 to 2022-10-03
| Draft SRS Docs v4.0 | 0% | 2022-10-10 | 2022-10-10 | bar: 2022-08-22 to 2022-10-10
| SRS_v4.0 - Revise User Stories + Features | 0% | 2022-10-10 | 2022-10-10 | bar: 2022-08-22 to 2022-10-10
| SRS_v4.0 - Revise Analysis models diagrams | 0% | 2022-10-10 | 2022-10-10 | bar: 2022-08-22 to 2022-10-10
| SRS_v4.0 - Database Model Class diagrams | 0% | 2022-10-10 | 2022-10-10 | bar: 2022-08-22 to 2022-10-10
| Initial UI Mock-Ups | 30% | 2022-09-30 | 2022-10-09 | bar: 2022-08-22 to 2022-10-09
| UI - Navbar | 100% | 2022-09-30 | 2022-09-30 | bar: 2022-08-22 to 2022-10-09
| UI - Landing Page | 100% | 2022-09-30 | 2022-10-04 | bar: 2022-08-22 to 2022-10-09
| UI - Footer | 100% | 2022-10-05 | 2022-10-05 | bar: 2022-08-22 to 2022-10-09
| UI - Connect Wallet layout | 100% | 2022-10-06 | 2022-10-06 | bar: 2022-08-22 to 2022-10-09
| UI - SideBar | 100% | 2022-10-06 | 2022-10-06 | bar: 2022-08-22 to 2022-10-09
| UI - Home page | 100% | 2022-10-06 | 2022-10-07 | bar: 2022-08-22 to 2022-10-09
| UI - NFT minting page | 100% | 2022-10-07 | 2022-10-07 | bar: 2022-08-22 to 2022-10-09
| UI - NFT Details page | 100% | 2022-10-08 | 2022-10-08 | bar: 2022-08-22 to 2022-10-09
| UI - NFT marketplace | 100% | 2022-10-08 | 2022-10-08 | bar: 2022-08-22 to 2022-10-09
| UI - NFT collection page | 100% | 2022-10-08 | 2022-10-08 | bar: 2022-08-22 to 2022-10-09
| UI - NFT transaction history page | 100% | 2022-10-08 | 2022-10-08 | bar: 2022-08-22 to 2022-10-09
| UI - NFT relist Component | 100% | 2022-10-08 | 2022-10-08 | bar: 2022-08-22 to 2022-10-09
| UI - Community page | 100% | 2022-10-09 | 2022-10-09 | bar: 2022-08-22 to 2022-10-09
| UI - Donation component | 100% | 2022-10-09 | 2022-10-09 | bar: 2022-08-22 to 2022-10-09
| UI - Searching component | 100% | 2022-10-09 | 2022-10-09 | bar: 2022-08-22 to 2022-10-09
| UI - Music player component | 100% | 2022-10-09 | 2022-10-09 | bar: 2022-08-22 to 2022-10-09
| UI Mock-Ups V2.0 | 100% | 2022-10-15 | 2022-10-16 | bar: 2022-08-22 to 2022-10-14
| UI_v2.0 - Landing Page | 100% | 2022-10-15 | 2022-10-15 | bar: 2022-08-22 to 2022-10-16
| UI_v2.0 - Home page | 100% | 2022-10-15 | 2022-10-15 | bar: 2022-08-22 to 2022-10-16
| UI_v2.0 - NFT collection page | 100% | 2022-10-15 | 2022-10-15 | bar: 2022-08-22 to 2022-10-16
| UI_2.0 - NFT Details page | 100% | 2022-10-16 | 2022-10-16 | bar: 2022-08-22 to 2022-10-16
| UI_2.0- Community page | 100% | 2022-10-16 | 2022-10-16 | bar: 2022-08-22 to 2022-10-16
| UI Mock-Ups V3.0 | 0% | 2022-10-20 | 2022-10-20 | bar: 2022-08-22 to 2022-10-20
Phase 2: Implementation
| Blockchain | 50% | 2022-10-10 | 2022-10-16 | 7 | bar: 2022-08-22 to 2022-10-13
| Setup Hardhat dev environment | 100% | 2022-10-10 | 2022-10-10 | bar: 2022-08-22 to 2022-10-14
| Setup Mumbai testnet | 100% | 2022-10-10 | 2022-10-10 | bar: 2022-08-22 to 2022-10-14
| Setup Alchemy RPC node | 100% | 2022-10-10 | 2022-10-10 | bar: 2022-08-22 to 2022-10-14
| Setup Etherscan API | 100% | 2022-10-11 | 2022-10-11 | bar: 2022-08-22 to 2022-10-14
| Setup testing environment | 100% | 2022-10-11 | 2022-10-11 | bar: 2022-08-22 to 2022-10-14
| Setup NFT.storage | 100% | 2022-10-12 | 2022-10-12 | bar: 2022-08-22 to 2022-10-14
| Smart Contract development | 25% | 2022-10-13 | 2022-10-16 | bar: 2022-08-22 to 2022-10-14
| Single NFT SC | 100% | 2022-10-13 | 2022-10-13 | 1 | bar: 2022-08-22 to 2022-10-14
| Multiple NFTs SC | 100% | 2022-10-14 | 2022-10-14 | 1 | bar: 2022-08-22 to 2022-10-14
| Marketplace SC | 0% | 2022-10-14 | 2022-10-15 | bar: 2022-08-22 to 2022-10-14
| Donation SC | 0% | 2022-10-15 | 2022-10-15 | 1 | bar: 2022-08-22 to 2022-10-14
| Membership SC | 0% | 2022-10-16 | 2022-10-16 | 1 | bar: 2022-08-22 to 2022-10-14
| Deploying scripts | 0% | 2022-10-16 | 2022-10-16 | bar: 2022-08-22 to 2022-10-14
| Blockchain V2 | 0% | 2022-10-20 | 2022-10-20 | 1 | bar: 2022-08-22 to 2022-10-20
| Revise Donation SC - unit test script | 0% | 2022-10-20 | 2022-10-20 | bar: 2022-08-22 to 2022-10-20
| Revise Marketplace SC - unit test script | 0% | 2022-10-20 | 2022-10-20 | bar: 2022-08-22 to 2022-10-20
| Revise Membership SC - unit test script | 0% | 2022-10-20 | 2022-10-20 | bar: 2022-08-22 to 2022-10-20
| Backend | 0% | 2022-10-17 | 2022-10-23 | bar: 2022-08-22 to 2022-10-23
| Setup Golang dev environment | 0% | 2022-10-17 | 2022-10-16 | bar: 2022-08-22 to 2022-10-23
| Setup database driver/connection | 0% | 2022-10-17 | 2022-10-17 | bar: 2022-08-22 to 2022-10-23
| Connect database driver to Golang server | 0% | 2022-10-17 | 2022-10-17 | bar: 2022-08-22 to 2022-10-23
| Setup JWT Service | 0% | 2022-10-17 | 2022-10-17 | bar: 2022-08-22 to 2022-10-23
| JWT service Unit Tests | 0% | 2022-10-17 | 2022-10-17 | bar: 2022-08-22 to 2022-10-23
| Setup User model | 0% | 2022-10-17 | 2022-10-17 | bar: 2022-08-22 to 2022-10-23
| Setup Supporter model | 0% | 2022-10-17 | 2022-10-17 | bar: 2022-08-22 to 2022-10-23
| Setup Marketplace model | 0% | 2022-10-17 | 2022-10-17 | bar: 2022-08-22 to 2022-10-23
| Setup Community model | 0% | 2022-10-17 | 2022-10-17 | bar: 2022-08-22 to 2022-10-23
| Setup User DAO -- interface & impl | 0% | 2022-10-18 | 2022-10-18 | bar: 2022-08-22 to 2022-10-23
| User Unit Tests | 0% | 2022-10-18 | 2022-10-18 | bar: 2022-08-22 to 2022-10-23
| Setup Supporter DAO -- interface & impl | 0% | 2022-10-19 | 2022-10-19 | bar: 2022-08-22 to 2022-10-23
| Supporter Unit Tests | 0% | 2022-10-19 | 2022-10-19 | bar: 2022-08-22 to 2022-10-23
| Setup Marketplace DAO -- interface & impl | 0% | 2022-10-20 | 2022-10-21 | bar: 2022-08-22 to 2022-10-23
| Marketpkace unit tests | 0% | 2022-10-21 | 2022-10-21 | bar: 2022-08-22 to 2022-10-23
| Setup Community DAO -- interface & impl | 0% | 2022-10-22 | 2022-10-23 | bar: 2022-08-22 to 2022-10-23
| Community Unit Tests | 0% | 2022-10-23 | 2022-10-23 | bar: 2022-08-22 to 2022-10-23
| Backend V2 - Revise servers | 0% | 2022-10-27 | 2022-10-27 | bar: 2022-08-22 to 2022-10-27
| Backend V3 - Revise servers | 0% | 2022-10-31 | 2022-10-31 | bar: 2022-08-22 to 2022-10-31
| Backend V4 - Revise servers | 0% | 2022-11-05 | 2022-11-05 | bar: 2022-08-22 to 2022-11-05
| Front-end && UI | 0% | 2022-10-24 | 2022-11-20 | 28 | bar: 2022-08-22 to 2022-11-20
| UI App content design | 0% | 2022-10-24 | 2022-10-30 | bar: 2022-08-22 to 2022-11-20
| Setup Rive | 0% | 2022-10-24 | 2022-10-24 | bar: 2022-08-22 to 2022-11-20
| Setup PottieFile | 0% | 2022-10-24 | 2022-10-24 | bar: 2022-08-22 to 2022-11-20
| Desgin Logo | 0% | 2022-10-24 | 2022-10-24 | bar: 2022-08-22 to 2022-11-20
| Desgin customized avatar | 0% | 2022-10-24 | 2022-10-25 | bar: 2022-08-22 to 2022-11-20
| Desgin customized buttons | 0% | 2022-10-25 | 2022-10-26 | bar: 2022-08-22 to 2022-11-20
| Desgin customized emoji reaction | 0% | 2022-10-26 | 2022-10-28 | bar: 2022-08-22 to 2022-11-20
| Design customized background svgs + pngs | 0% | 2022-10-28 | 2022-10-30 | bar: 2022-08-22 to 2022-11-20
| Front-end implementation | 0% | 2022-10-31 | 2022-11-20 | bar: 2022-08-22 to 2022-11-20
| env - Setup NextJS | 0% | 2022-10-31 | 2022-10-31 | bar: 2022-08-22 to 2022-11-20
| env - Setup TailwindCSS | 0% | 2022-10-31 | 2022-10-31 | bar: 2022-08-22 to 2022-11-20
| env - Setup NFT.storage API | 0% | 2022-10-31 | 2022-10-31 | bar: 2022-08-22 to 2022-11-20
| env - Setup IPFS client | 0% | 2022-10-31 | 2022-10-31 | bar: 2022-08-22 to 2022-11-20
| env - Setup Rainbowkit -- Wallet Connector | 0% | 2022-10-31 | 2022-10-31 | bar: 2022-08-22 to 2022-11-20
| env - Setup Ethers.js | 0% | 2022-10-31 | 2022-10-31 | bar: 2022-08-22 to 2022-11-20
| env - Setup Moralis Provider | 0% | 2022-10-31 | 2022-10-31 | bar: 2022-08-22 to 2022-11-20
| env - Setup Redux | 0% | 2022-10-31 | 2022-10-31 | bar: 2022-08-22 to 2022-11-20
| impl - Navbar | 0% | 2022-11-01 | 2022-11-01 | bar: 2022-08-22 to 2022-11-20
| impl - Footer | 0% | 2022-11-01 | 2022-11-01 | bar: 2022-08-22 to 2022-11-20
| impl - Connect Wallet layout | 0% | 2022-11-01 | 2022-11-01 | bar: 2022-08-22 to 2022-11-20
| impl - Landing Page | 0% | 2022-11-01 | 2022-11-04 | bar: 2022-08-22 to 2022-11-20
| impl - SideBar | 0% | 2022-11-04 | 2022-11-04 | bar: 2022-08-22 to 2022-11-20
| impl - Home page | 0% | 2022-11-04 | 2022-11-05 | bar: 2022-08-22 to 2022-11-20
| impl - Profile/Edit page | 0% | 2022-11-06 | 2022-11-07 | bar: 2022-08-22 to 2022-11-20
| impl - NFT minting page | 0% | 2022-11-08 | 2022-11-08 | bar: 2022-08-22 to 2022-11-20
| impl - Music player component | 0% | 2022-11-09 | 2022-11-09 | bar: 2022-08-22 to 2022-11-20
| impl - NFT collection page | 0% | 2022-11-10 | 2022-11-12 | bar: 2022-08-22 to 2022-11-20
| impl - NFT Details page | 0% | 2022-11-13 | 2022-11-13 | bar: 2022-08-22 to 2022-11-20
| impl - NFT transaction history page | 0% | 2022-11-14 | 2022-11-14 | bar: 2022-08-22 to 2022-11-20
| impl - NFT relist page | 0% | 2022-11-14 | 2022-11-14 | bar: 2022-08-22 to 2022-11-20
| impl - Donation component | 0% | 2022-11-15 | 2022-11-15 | bar: 2022-08-22 to 2022-11-20
| impl - Searching component | 0% | 2022-11-16 | 2022-11-17 | bar: 2022-08-22 to 2022-11-20
| impl - Membership plan page | 0% | 2022-11-17 | 2022-11-17 | bar: 2022-08-22 to 2022-11-20
| impl - Community page | 0% | 2022-11-18 | 2022-11-20 | bar: 2022-08-22 to 2022-11-20
| impl - My Supporters page | 0% | 2022-11-20 | 2022-11-20 | bar: 2022-08-22 to 2022-11-20
Phase 5: Testing and Deployment
| System Testing | 0% | 2022-11-21 | 2022-11-24 | 4
| Deployment Through Vercel | 0% | 2022-11-25 | 2022-11-28 | 4
| Final Presentation | 0% | 2022-11-29 | 2022-12-04 | 6
| Final Project Artifact Submission (Blackboard) | 0% | 2022-12-04 | 2022-12-04 | 1
Insert new rows ABOVE this one
| SIMPLE GANTT CHART by Vertex42.com |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
Note on G6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.